## Sheet1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header |  |  |  | Ngoc | [5 empty] | NGỌC
Carousel |  |  |  | Ngoc
About Us |  |  |  | Ngoc
Products |  |  |  | Ngoc
Sevices |  |  |  | Ngoc
Build project + Invite member | 25/05 | 25/05 | 100% | Thế | 25/05 | 25/05 | 100% | Thế | BEGIN | THẾ
Upload tài nguyên | 28/05 | 28/05 | 100% | Thế | 28/05 | 28/05 | 100% | Thế | Upload file html, css, image, libs, distribution
Upload section PROJECT | 29/05 | 29/05 | 100% | Thế | 29/05 | 29/05 | 100% | Thế | Build khung sườn cho index
Edit section PROJECT | 31/05 | 31/05 | 100% | Thế | 31/05 | 31/05 | 100% | Thế | Code index, css cho section PROJECT
Upload + Edit section PROGRESS | 2022-02-06 | 2022-02-06 | 100% | Thế | 2022-02-06 | 2022-02-06 | 100% | Thế | Code index,css cho section PROGRESS
Upload section TESTIMONIAL | 2022-02-06 | 2022-02-06 | 100% | Thế | 2022-02-06 | 2022-02-06 | 100% | Thế | Build khung sườn cho index
Edit section TESTIMNONIAL | 2022-04-06 | 2022-04-06 | 100% | Thế | 2022-04-06 | 2022-04-06 | 100% | Thế | Code index,css cho section TESTIMONIAL
Upload section BLOG, FOOTER | 2022-04-06 | 2022-04-06 | 100% | Thế | 2022-04-06 | 2022-04-06 | 100% | Thế | Build khung sườn cho BLOG, FOOTER
Upload Light, Dark Theme | 2022-05-06 | 2022-05-06 | 100% | Thế | 2022-05-06 | 2022-05-06 | 100% | Thế | Upload Theme lên server
Nhánh dthe: check commit history | 2022-11-06 | 2022-11-06 | 100% | Thế | 2022-11-06 | 2022-11-06 | 100% | Thế | Check commit history, commit từ đầu đến giờ
Nhánh historyThe_1: check commit history | 2022-11-06 | 2022-11-06 | 100% | Thế | 2022-11-06 | 2022-11-06 | 100% | Thế | Check commit history, commit từ đầu đến giờ
Nhánh d_the: nhánh merge vô main | 2022-11-06 | 2022-11-06 | 100% | Thế | 2022-11-06 | 2022-11-06 | 100% | Thế | Nhánh chính merge vô main, do những nhánh cũ bị lỗi không merge được vô main nên đã tạo nhánh mới
Build deploy, screen video, upload project link to Cybersoft | 2022-12-06 | 2022-12-06 | 100% | Thế | 2022-12-06 | 2022-12-06 | 100% | Thế | FINISH